## IHE WP-Timeline
Health IT Standards for Health Information Management (HIM) Practices: Timeline
Project Period: October 23, 2014 through August, 2015
Tasks | POC | 2014 |  | 2015 | [11 empty] | Deliverable
|  | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Project Management Tasks | bar: 2015 Mar to 2015 Dec
HIT Standards for HIM Practices White Paper Staff Calls | IHE White Paper | 11/24 | 12/08 - 12/22 | 1/05 - 1/19 | 2/2 - 2/16 | 3/02 - 3/16 - 3/30 | 4/13 - 4/27 | 5/11 - 5/25 | 6/08 - 6/22 | 7/06 - 7/20 | 8/03 - 8/17 - 8/31
ITI Planning Domain: HIT Standards for HIM Practices White Paper project call | IHE White Paper |  | 12/01 - 12/15 - 12/29 | 1/12 - 1/26 | 2/09 - 2/23 | 3/09 - 3/23 | 4/06 - 4/20 | 5/04 -5/18 | 6/01 - 6/15 - 6/29 | 7/13 - 7/27 | 8/10 - 8/24 | 2014-09-07
External Review 1) Guidance on the project activities (2) Review of project deliverables | Advisory Committee | 2015 Feb: 2014-02-01; 2015 Aug: 2014-08-31
Activities 2, 4, 5, 7: Contribute to the development of the project deliverables | Consultant/Contractor | [14 empty] | Define timeline for consulant/contractor
Project Tasks
Objective 1. 0. Prepare foundation for White Paper proposal
1.1 Set up Wiki and maintain | Diana | 2014 Dec: 12/16; 2015 Jan: 1/31
1.2 Literature Review | Harry | 2014 Nov: 11/10; 2015 Apr: 4/30
1.3 Project Planning (Develop Outline for White Paper) | Harry | 2015 Jan: 1/1 - 1/31
Objective 2. 0. Developing methodology, modeling, mapping, field testing, and data collection
2.1 Develop methodology for comparison of HIM Practices and IHE Standards: | Harry | 2014 Dec: 12/1 - 12/31 | 1. Proposed methodology 2. Proposed Comparison Table
2.1.1 Identify HIM Practices for Availability and Data Integrity in the Literature | Harry | 2015 Feb: 2/10/2015; 2015 Apr: 4/30/2015
2.1.2 Identified IHE Standards that support the practice | Harry | 2015 Feb: 2/10/2015; 2015 Apr: 4.30/2015
2.1.3 Retract Use Case from existing standards. | Harry | 2015 Feb: 2/10/2015; 2015 Apr: 4/30/2015
2.1.4 Align Use Case with HIM Practice | Harry | 2015 Feb: 2/10/2015; 2015 Apr: 4/30/2015
2.2 Internal Review Select external review SMEs. (Deb Green, Julie Dooling) validate methodolgy. Validate methodogy, validate comparison. Developers of table vs review current table. | Harry | 2014 Dec: 12/15/2014; 2015 Jan: 1/10/2015 | 1. Validated methodolgy 2. Valdate the comparison table.
2.2.1 Recruit External SME by Jan 10th- 1. Devlopers - Reviewers | Harry | 2014 Dec: 12/01/2014; 2015 Jan: 1/10/2015 | Recruit External SME
2.3 Conduct Gap Analysis and complete the table defined in 2.1 - 2.2, including prioritization of identified gaps, creation of the list of use cases and the roadmap for the development of HIT interoperability standards for HIM practices/checklist. | Harry | 2015 Mar: 3/1; 2015 Apr: 4/30 | Completed table
2.4 Model the outcome of the HIM Practice - HIT Standards mapping (table completed in 2.3 ) Model the outcomes to the mapping into the HL7 Record Lifecycle model standard. | Harry | 2015 Jan: 1/15/2015; 2015 Mar: 3/31/15 | Complete modeling between outcomes of HIM Practice-IHE Standards and HL7 Record Lifecycle.
2.5 Develop the roadmap for HIT Standards for HIM Practice based on the outcome of activties in 2.3 and 2.4 . | Harry | 2015 Feb: 2/01/15; 2015 Apr: 4/30/2015 | Completed roadmap
2.6 Publish the White Paper: 1 - Public Review, 2 - Comment Reconcilation 3 - Final Public | Harry | 2015 Jun: 6/30/2015; 2015 Aug: 8/15/2015
3.0 Communication, outreach, & marketing
3.0.1 JAHIMA Publication Submission date and publicaiton date | Harry & Diana | 11/28/14- 1/20/2015 | 12/29/14- 2/17/15 | 1/29/15- 3/24/15 | 2/25/15- 4/21/15 | 4/02/15- 5/26/15 | 5/01/15- 6/23/15 | 5/28/15- 7/21/15 | 6/24/15- 8/18/15 | 7/23/15- 9/15/15 | 8/27/15- 10/20/15
4.0.2 Webinar submission date and publication | Harry & Diana | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD
Project Wiki URL: http://wiki.ihe.net/index.php?title=HIT_Standards_for_HIM_Practices#Working_Documents
Project Team: Harry Rhodes, Principal Investigator, Project Director; Diana Warner, Stakeholder Engagement, Communication, Outreach and Marketing; Sheryl Reyes, Manager Standards.