## Sheet2
2013
|  | January | February | March | April | May | June | July | August | September | October | November | December
2013 | NA Connectathon | January: 2013-01-28
2013 | HIMSS Showcase | March: 2013-03-04
2013 | AMMI Exhibit | 2013 June: 2013-06-01
| 2013 Fall F2F | 2013 October: 10/8 - 10/11 Boca Raton
Cycle 8 | New Supplements | bar: January to 2013 August
Cycle 9 | Update TI Supplements | bar: February to 2013 June
Cycle 8 | Final Text Update | 2013 June: 2013-06-14
Cycle 8 | Whitepapers | bar: 2013 July to 2013 November
Cycle 9 | New Proposals | bar: 2013 August to 2013 December
Prep for Connectathon | bar: January; 2013 November to 2013 December
2014
|  | January | February | March | April | May | June | July | August | September | October | November | December
2014 | NA Connectathon | January: 1/27/2013 Chicago
2014 | HIMSS Showcase | February: 2/23/2013 Orlando
2014 | AMMI Exhibit | May: 5/31/2013 Philadelphia
2014 Spring F2F
Cycle 9 | New Supplements | bar: January to 2014 August
Cycle 9 | Update TI Supplements | bar: February to 2014 June
Cycle 9 | Final Text Update | 2014 June: 2013-06-14
Cycle 9 | Whitepapers | bar: 2014 July to 2014 November
Cycle 10 | New Proposals | bar: 2014 August to 2014 December
Prep for Connectathon | bar: January; 2014 November to 2014 December
Cycle 9 Call for new Proposals
| Open Call | January: 2013-08-01; February: 30 days before close
| PC webex to vet requests | January: 2013-09-09; February: 4 weeks before ballot
| Close Call | January: 2013-09-30
| Open PC Brief Ballot | January: 2013-09-30; February: 1 week before F2F
| PC F2F | January: 2013-10-07
| Close PC Brief Ballot | January: 2013-10-14; February: 1 week after F2F
| TC starts analysis | January: 2013-10-14; February: 1 week after F2F
| TC detailed proprosal due | January: 2013-11-11; February: 4 week analysis
| Open TC detailed ballot | January: 2013-11-11
| Close TC detailed ballot | January: 2013-11-25; February: 2 week ballot
Cycle 9 New Supplements
| start | January: 2013-12-27; February: Assume 150 days of work
| submit to TC for ballot | January: 2014-05-26
| end TC ballot | January: 2014-06-09; February: 2 week ballot
| start update from ballot comments | January: 2014-06-09
| end update from comments | January: 2014-06-23; February: give 2 weeks for updates
| Submit to IHE for public comment | January: 2014-06-23; February: Assume this will occur last week of June
| Publish for public commnent | January: 2014-06-30; February: 1 week after submission to IHE
| End public comment | January: 2014-07-30; February: Public comment is 30 days, start immediately after (comments may trickle in over the 30 days)
| Start Update from comments | January: 2014-07-30; February: start immediately after PC (comments may trickle in over the 30 days)
| End update from comments | January: 2014-08-13; February: 2 weeks to update from comments
| Submit to IHE for Trial Implementation | January: 2014-08-13
| Publish for Trial Implementation | January: 2014-08-20; February: 1 week after submission to IHE
Cycle 9 Update TI Supplements / FT
| solicit and document CP's | January: 2014-04-09; February: 30 days
| TC ballot CP's | January: 2014-05-09
| end TC ballot | January: 2014-05-23; February: 2 week ballot
| start update from ballot comments | January: 2014-05-23
| end update from comments | January: 2014-06-06; February: give 2 weeks for updates
| Submit to IHE for Trial Implementation | January: 2014-06-06; February: Assume this will occur second week of June
| Publish for Trial Implementation | January: 2014-06-13; February: 1 week after submission to IHE
Note on C11: Merritt, Steve: (Can float because there is no Connectathon deadline)
Note on C25: Merritt, Steve: (Can float because there is no Connectathon deadline)