IHE Cardiology Technical Committee 2011/2012

Action Item and Planning Document

Action Items

| ID | Due | Description | Owner | Status | Comments |
| --- | --- | --- | --- | --- | --- |
| 20111213.1 | Jan. 6 | Get meeting minutes out | Antje/ Tom | Done |  |
| 20120104.1 | Jan. 6 | Request updates to ACC report from Dr. Tcheng | Tom | Done |  |
| 20120104.2 | Jan. 6 | Get new IHE profile templates distributed to Nick/Bryan | Tom | Done |  |
| 20120125.1 | Jan. 27 | Publish Schedule on the wiki | Antje | Done |  |
| 20120125.2 | Feb. 2 | Provide Key Data Elements spreadsheet with assigned sections to the team | Nick | In Progress |  |
| 20120201.1 | Feb 2 | distribute detailed terminology spreadsheet to the the volunteers for next-week's CDA-Cath review | Nick | NEW |  |
| 20120201.2 | Feb 2 | distribute C-CDA link to group | Harry | NEW | Need to sign NDA on HL7 site |
| 20120201.3 | Feb 2 | clarify with Dr. Tcheng that his ACC initiative is the same one as the "Update to Cath lab standards" referred to in November by Joel Harder | Tom | NEW |  |
| 20120201.4 | Feb 2 | post the current Cath Vol WIP on the ftp site | Tom | DONE |  |

Schedule

| ID | Due | Topic | Owner | Status | Comments |
| --- | --- | --- | --- | --- | --- |
| 20120125.3 | Feb.1 | Volume 1 Content CRC | Tom/ Antje | In Progress |  |
| 20120125.4 | Feb. 1 | Volume 1 Content EPRC | Bryan | In Progress |  |
| 20120125.5 | Feb. 8 | Assessment and Plan (CRC) | Nick | Open |  |
| 20120125.6 | Feb. 8 | Complications and adverse Events | Tom | Open |  |
| 20120125.7 | Feb. 8 | Family History | Nick | Open |  |
| 20120125.8 | Feb. 8 | Header | Nick/ Tom | Open |  |
| 20120125.9 | Feb. 8 | Medical History | Nick | Open |  |
| 20120125.10 | Feb. 8 | Allergies | Nick | Open |  |
| 20120125.11 | Feb. 8 | Social History | Nick | Open |  |
| 20120125.12 | Feb. 8 | Vital Signs | Nick | Open |  |
| 20120125.13 | Feb. 15 | Assessment and Plan (EPRC) | Bryan | Open |  |
| 20120125.14 | Feb. 15 | Complications and adverse Events | Bryan | Open |  |
| 20120125.15 | Feb. 15 | Family History | Duncan | Open |  |
| 20120125.16 | Feb. 15 | Header | Duncan | Open |  |
| 20120125.17 | Feb. 15 | Medical History | Duncan | Open |  |
| 20120125.18 | Feb. 15 | Allergies | Duncan | Open |  |
| 20120125.19 | Feb. 15 | Social History | Bryan | Open |  |
| 20120125.20 | Feb. 15 | Vital Signs | Bryan | Open |  |
| 20120125.21 | Feb. 22 | Medications Administered (CRC) | Harry | Open |  |
| 20120125.22 | Feb. 22 | Prior Results | Nick | Open |  |
| 20120125.23 | Feb. 22 | Procedure Description Cath | Paul | Open |  |
| 20120125.24 | Feb. 22 | Procedure Findings Cath | Nick | Open |  |
| 20120125.25 | Feb. 22 | Service Events | Nick | Open |  |
| 20120125.26 | Feb. 29 | Medications Administered (EPRC) | Bryan | Open |  |
| 20120125.27 | Feb. 29 | Prior Results | Bryan | Open |  |
| 20120125.28 | Feb. 29 | Procedure Description Ablation | Anthony | Open |  |
| 20120125.29 | Feb. 29 | Procedure Findings Ablation | Anthony | Open |  |
| 20120125.30 | Feb. 29 | Procedure Description ICD | Duncan/Anthony | Open |  |
| 20120125.31 | Feb. 29 | Procedure Findings ICD | Duncan/Anthony | Open |  |
| 20120125.32 | Feb. 29 | Service Events | Bryan | Open |  |
| 20120125.33 | March 7 | Procedure Description PCI | Paul | Open |  |
| 20120125.34 | March 7 | Procedure Findings PCI | Nick | Open |  |
| 20120125.35 | March 14 | Procedure Description Ablation | Anthony | Open |  |
| 20120125.36 | March 14 | Procedure Findings Ablation | Anthony | Open |  |
| 20120125.37 | March 14 | Procedure Description ICD | Duncan/Anthony | Open |  |
| 20120125.38 | March 14 | Procedure Findings ICD | Duncan/Anthony | Open |  |