## IHE WP-Timeline
Health IT Standards for Health Information Management (HIM) Practices: Timeline
Project Period: October 23, 2014 through August, 2015
Tasks | POC | 2014 |  |  | 2015 | [16 empty] | Deliverable
|  | Nov | Dec |  | Jan |  | Feb |  | Mar |  | Apr |  | May |  | Jun |  | Jul |  | Aug |  | Sep
Project Management Tasks
AHIMA Team Calls | Diana | 11/24 | 12/8 |  | 1/5 | 2015-01-19 | 2015-02-02 | 2015-02-12 | 2015-02-02 | 2015-02-12 | 2015-04-09 | 2015-04-13 | 2015-05-07 | 2015-05-21 | 2015-06-04 | 2015-06-22 | 2015-07-06 | 2015-07-16 | 2015-08-03 | 2015-08-13
ITI Planning Committee Call | Eric/Harry |  | 12/1 | 12/15 | 2015-01-12 | 2015-01-26 | 2015-02-05 | 2015-02-19 | 2015-03-05 | 2015-03-19 | 2015-04-02 | 2015-04-16 | 2015-05-14 | 2015-05-28 | 2015-06-11 | 2015-06-25 | 2015-07-09 | 2015-07-23 | 2015-08-06 | 2015-08-20 | 2015-09-03
SMEs Calls | Diana/Harry | [5 empty] | 2015-02-09 | 2015-02-23 | 2015-03-09 | 2015-03-23 | 2015-04-06 | 2015-04-20 | 2015-05-04
Project Tasks
Objective 1. 0. Prepare foundation for White Paper proposal
1.1 Set up Wiki and maintain | Diana |  |  | 12/16 |  | 1/31 | [15 empty] | COMPLETED
1.2 Literature Review | Harry | 11/10 |  |  |  |  | 2015-03-23: 2015-03-31
1.3 Project Planning | Harry |  |  |  |  | 2015-01-31 | [15 empty] | COMPLETED
Objective 2.0 Develop HIM Checklist, Select HIT Standards for HIM Practices
2.1Review by Initial Project Team 1) Methodology (Table columns A-D) 2) Schedule and Deliverables | Project Team |  |  | 12/1 - 12/31 | [17 empty] | 1. Proposed methodology 2. Proposed Comparison Table: COMPLETED
2.2 Recruit External SME | Harry |  |  | 2015-12-01 |  | 2015-01-10 | [15 empty] | COMPLETED
2.3 Document HIM best practices for (a) Integrity; (b) Protection; (c) Availability (Column A) | Harry | [5 empty] | 2015-02-09: 2015-02-09; 2015-02-23: 2015-02-28 | [8 empty] | COMPLETED
2.4 SME Review of Column A | [6 empty] | 2015-02-09: 2015-02-09; 2015-03-23: 2015-03-31 | [8 empty] | COMPLETED
2.5 Define Use Cases for selected HIM practices (Column B) | Harry | [5 empty] | 2015-02-09: 2015-02-10; 2015-03-23: 2015-03-31 | [8 empty] | COMPLETED
2.6 SME Review of Column B | [6 empty] | 2015-02-23: 2015-02-23; 2015-04-06: 2015-04-15 | [8 empty] | COMPLETED
2.7 ITI Complete Columns C&D | [6 empty] | 2015-03-09: 2015-03-10; 2015-04-20: 2015-04-30 | [8 empty] | COMPLETED
2.8 SME Review Columns A-D | [6 empty] | 2015-03-23: 2015-03-15; 2015-05-04: 2015-05-15 | [8 empty] | COMPLETED
Objective 3.0 Develop White Paper
3.0 WP development | [5 empty] | 2015-01-01 | 2015-03-09: 2015-03-04; 2015-04-20: 2015-04-30 | [8 empty] | COMPLETED
3.1 SME Review draft | [6 empty] | 2015-03-09: 2015-03-10; 2015-05-04: 2015-05-04 | [8 empty] | COMPLETED
3.2 ITI PC Review Draft | [6 empty] | 2015-03-23: 2015-03-31 | 2015-05-31 | [7 empty] | COMPLETED
3.3 Publish the White Paper: 1 - Public Review, 2 - Comment Reconcilation 3 - Publish | Harry | [13 empty] | 2015-06-01 |  |  |  |  | 2015-08-15 |  | COMPLETED
3.4 Develop proposal for the IHE 2015-16 development cycle | Harry | [18 empty] | 2015-08-15 | 2015-09-15 | COMPLETED
Objective 4.0 Communication, Outreach and Marketing
4.0 JAHIMA Publication: Submission 5/28, publication August 2015 | Harry & Diana | [5 empty] | 2015-03-09: 2015-03-09 | 2015-05-28 |  |  |  |  | 2015-08-01 |  |  | COMPLETED
3.0.2 Convention Presentation: Submission 6/15, presentation 9/29 | Harry & Diana | 2015-11-15 | [12 empty] | 2015-06-01 |  |  | 2015-07-31 |  |  | 2015-09-29 | COMPLETED
Project Wiki URL: http://wiki.ihe.net/index.php?title=HIT_Standards_for_HIM_Practices#Working_Documents
Project Team: Harry Rhodes, Principal Investigator, Project Director; Diana Warner, Stakeholder Engagement, Communication, Outreach and Marketing; Sheryl Reyes, Manager Standards.